## Cover Page
Grocery shopping and Delivery management
Unit Test Cases
aaa
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Sakshi Gupta/Md. Siddiq | Ashu Jauhari
| Role | Trainee | Trainer
| Signature | Sakshi Gupta /Md. Siddiq | Ashu Jauhari
| Date | 2020-03-12 | 2020-03-12
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Test Case details
Unit Test Cases Grocery shopping and Delivery management Project ID: B029 C3: Protected Controlled Copy
Test Cases and Log
Test Type : | Unit Testing | Date: | 2020-03-12
Purpose & Scope:
< This section describes the purpose and scope of the project>
Test Pre-requisites:
< This section describes the Pre requisites for testing this project>
Instructions
Test case Id : Mention the test case Id Test Case: Mention the Test case description Steps to execute the test case: Mention the list of steps to execute the test case Expected Result: Mention the expected result. All the columns upto this should be filled during the design. Test Date:Mention the date the test case is tested. The columns after this should be filled during unit testing Actual Result: Mention the actual results. Include the test result proof as snapshots and include it as objects. Pass/Fail: Mention the test results Defect Id: If the test case fails, then FAIL must be indicated and the defect ID needs to be filled up. Defect Tracking can be done and tracked in the columns Defect Test 1, Defect Test 2 etc. Maximum of 2 reopens are provided in the defect tracking. If the defect is not closed within that, then a new defect should be opened.
Terms and Conditions
Disclaimer: Please do not circulate or distribute this document outside of Cognizant Network, We have a Zero Tolerance Policy. Kindly adhere to 100% Compliance at all times.

## Test Cases & Log
Unit Test Cases Grocery shopping and Delivery mgmt Project ID: B029 C3: Protected Controlled Copy
Test Case ID | Test Case | Steps to execute the test case | Expected Result | Test Date | Actual Result | PASS / FAIL | Defect ID | Retest Date | Actual Result | PASS / FAIL | DefectStatus | Retest Date | Actual Result | PASS / FAIL | DefectStatus | Retest Date | Actual Result | PASS / FAIL | DefectStatus
US_1 :User Registration | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
1 | Check User should be able to Register. | 1>> click on register button 2>> Mendatory fields are: First Name Last Name DoB Gender Contact Number User Id Password 3>>Click on Submit button | New user created successfully. | 2020-06-03 | New user created successfully. | PASS
US_2 :User Authentication | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
2.1 | Check User should be able to Login. | 1>> click on Sign In button 2>> Mendatory fields are: User Id Password 3>>Click on Submit button | LogIn successfully | 2020-06-03 | LogIn successfully | PASS
2.2 | If User ID is not present | 1>> click on Sign In button 2>> Mendatory fields are: User Id Password 3>>Click on Submit button | User ID not present. | 2020-06-03 | User ID not present. | PASS
2.3 | For Wrong Password. | 1>> click on Sign In button 2>> Mendatory fields are: User Id Password 3>>Click on Submit button | Password not matching. | 2020-06-03 | Password not matching. | PASS
US_3 :Admin credentials | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
3.1 | Check Admin should be able to Login. | 1>> click on Sign In button 2>> Mendatory fields are: User Id Password 3>>Click on Submit button | Login successfully. | 2020-06-03 | LogIn successfully | PASS
3.2 | If UserID and Password does not match | 1>> click on Sign In button 2>> Mendatory fields are: User Id Password 3>>Click on Submit button | User ID not present. Password not matching. | 2020-06-03 | UserID & Password not matching. | PASS
US_4 :Help | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
4.1 | Check User should be able to get help. | 1>> Click on Help button 2>> Mendatory fields are: Issue Description 3>>Click on Send button | Display the Contact number | 2020-06-03 | Display the Contact number | PASS
US_5 : Feedback Questionnaire | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
5.1 | Check Admin should be able to create feedback Questionnaire . | 1>>click on the add question button | Question added successfully | 2020-06-03 | Question added successfully | PASS
US_6: User Feedback | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
6.1 | Check User should be able to submit feedback. | 1>>click on the feedback button 2>>click on Submit button | Feedback submitted successfully | 2020-06-03 | Feedback submitted successfully | PASS
US_7: Trigger Review | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
7.1 | Check As a system, I should be able to trigger review / feedbacks | 1>>click on the feedback button 2>>click on Submit button | Feedback submitted successfully | 2020-06-03 | User is not able to submit feedback | FAIL | DFT001 | 2020-06-03 | Feedback submitted successfully | PASS
US_8:Log off | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
8.1 | Check User should be able to Log off. | 1>>click Logout button | Logout Successfully. | 2020-06-03 | Logout Successfully. | PASS
US_9:Password reset | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
9.1 | Check User should be able to reset password. | 1>>Click on Forgot Password link 2>> Mendatory fields are: User Id Secret Question | Password Changed Successfully. | 2020-06-03 | Password Changed Successfully. | PASS
US_10: Item Selection | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
10.1 | Check User should be able to select items. | 1>>clicks on the “Item” link 2>>Select items | Item Selected Successfully | 2020-12-03 | User is not able to select the items. | FAIL | DFT001 | 2020-12-03 | Item Selected Successfully | PASS
US_11:Order management | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
11.1 | Check Admin should be able to manage the order . | 1>> click on order details button | Your orders are submitted successfully | 2020-12-03 | Your orders are submitted successfully | PASS
US_12:Payment | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
12.1 | Check User should be able to pay. | 1>>click on the “Online payment” button 2>>Payment Methods: Cash on Delivery Debit/Credit Card | Payment Successful. | 2020-12-03 | User is not able to pay for the order. | FAIL | DFT001 | 2020-12-03 | Payment Successful. | PASS
US_13:Delivery Agents | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
13.1 | Check Admin should be able to assign the agents to purchase the order. | 1>>click on Add / update Delivey agent details | Agent assigned Successfully | 2020-12-03 | Agent assigned Successfully | PASS
US_14:Address details | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
14.1 | Check User should be able to give the address details | 1>>click on the “address details” link 2>>add the address | Address added Successfully | 2020-12-03 | Address added Successfully | PASS
US_15: Finalise order | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
15.1 | Check User should be able to finalise the order | 1>>clicking on the “Finalize order” button | Order has been Finalized | 2020-12-03 |  | PASS
US_16:User details | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
16.1 | Check user should be able to add their details | 1>>Click on user details button | user details added successfully | 2020-12-03 | user details added successfully | PASS
US_17:Reviews | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
17.1 | Check user should be able to view the reviews | 1>> clicking on the “Reviews” button | View the reviews | 2020-12-03 | User is able to view the reviews. | PASS
US_18:Customer receives order | [7 empty] | Defect Test 1 |  |  |  | Defect Test 2 |  |  |  | Defect Test 3
18.1 | Check User should be able to receive the items send by the agent | 1>>message sent | Order delivered | 2020-12-03 | Order delivered | PASS

## Change Log
Change Log
Please note that this table needs to be maintained even if a Configuration Management tool is used.
Version Number | Changes made
V1.0.0 | <First version>
V1.1.0 | <If the change details are not explicitly documented in the table below, reference should be provided here>
| Page No | Changed by | Effective Date | Changes Effected
| 3 | Mithun Kumar | 2020-03-06
V1.2.0 | <If the change details are not explicitly documented in the table below, reference should be provided here>
| Page No | Changed by | Effective Date | Changes Effected
| 3 | Md. Siddiq | 2020-03-12