## Cover Page
Grocery shopping and Delivery management
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Sakshi Gupta/Mithun Kumar | Ashu Jauhari
| Role | Trainee | Trainer
| Signature | Sakshi Gupta/Mithun Kumar | Ashu Jauhari
| Date | 2020-03-12 | 2020-03-12
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog Grocery shopping and Delivery management Project ID: B029 C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog Grocery shopping and Delivery management Project ID: B029 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | User Registration | 8
Task_1 | Create Home Page with login and registration |  | Md. Siddiq |  | 4 | 2 | 2 | 0 | 0 | 0
Task_2 | Registration form |  | Md. Siddiq |  | 5 | 0 | 2 | 1 | 2 | 0
Task_3 | Create table |  | Mithun Kumar |  | 2 | 1 | 1 | 0 | 0 | 0
Task_4 | Post-successful field validation |  | Mithun Kumar |  | 4 | 1 | 1 | 2 | 0 | 0
Task_5 | save data in the database |  | Mithun Kumar |  | 5 | 1 | 2 | 1 | 1 | 0
User Story #2 | User Authentication | 8
Task_1 | Design Login page |  | Sakshi gupta |  | 6 | 2 | 2 | 1 | 1 | 0
Task_2 | Develop authentication process for login |  | Mayank |  | 4 | 1 | 2 | 1 | 0 | 0
Task_3 | Develop code for authentication process for login |  | Mayank |  | 4 | 1 | 2 | 1 | 0 | 0
User Story #3 | Admin credentials | 13
Task_1 | Create table to store admin details |  | Abhijeet |  | 5 | 1 | 1 | 2 | 1 | 0
Task_2 | Code to develop authentication of admin |  | Abhijeet |  | 6 | 2 | 2 | 0 | 2 | 0
Task_3 | code to develop Sucessful if user found |  | Abhijeet |  | 5 | 1 | 1 | 2 | 1 | 0
Task_4 | code to develop uncessful login if user not found in db |  | Abhijeet |  | 6 | 0 | 0 | 2 | 0 | 4
User Story #4 | Help | 13
Task_1 | Create Help page |  | Mayank |  | 4 | 0 | 0 | 2 | 2 | 0
Task_2 | Design form to report technical problm |  | Mayank |  | 4 | 0 | 0 | 0 | 1 | 3
Task_3 | portal t display contact details |  | Mayank |  | 5 | 0 | 1 | 1 | 2 | 1
Task_4 | All necessary constraint |  | Mayank |  | 4 | 0 | 0 | 0 | 2 | 2
User Story #5 | Feedback Questionnaire | 13
Task_1 | Create DataBase For Feedback |  | Sakshi gupta |  | 6 | 1 | 0 | 0 | 2 | 3
Task_1 | Review Page for Delivery/servicees |  | Sakshi gupta |  | 6 | 1 | 0 | 0 | 2 | 3
User Story #6 | User Feedback | 13
Task_1 | User feedback / reviews page |  | Sakshi gupta |  | 7 | 0 | 2 | 2 | 2 | 1
User Story #7 | Trigger Review | 13
Task_1 | Business logic check for user after login |  | Md. siddiq |  | 5 | 2 | 0 | 1 | 2 | 0
Task_2 | User Review on product |  | Md. Siddiq |  | 6 | 0 | 2 | 2 | 1 | 1
User Story #8 | Log off | 13
Task_1 | User Logout Sucessfully |  | Md. Siddiq |  | 6 | 2 | 0 | 0 | 2 | 2
User Story #9 | Password reset | 13
Task_1 | Create dataBase For password rest |  | Mithun Kumar |  | 5 | 2 | 2 | 0 | 0 | 1
Task_2 | Foget password |  | Mithun Kumar |  | 6 | 2 | 2 | 0 | 0 | 2
Task_3 | Bussiness logic to check valid user |  | Mithun Kumar |  | 5 | 0 | 2 | 1 | 0 | 2
Task_4 | Data will be saved in Db |  | Mithun Kumar |  | 4 | 0 | 2 | 1 | 0 | 1
TOTAL |  |  |  |  | 129 | 15 | 19 | 23 | 26 | 26

## Sprint -2
Sprint Backlog Grocery shopping and Delivery management Project ID - B029 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #10 | Item Selection | 13
Task_1 | Create dataBase For items |  | Md. Siddiq |  | 4 | 2 | 0 | 2 | 0 | 0
Task_2 | create page for items |  | Md. Siddiq |  | 5 | 0 | 0 | 1 | 2 | 2
User Story #11 | Order management | 13
Task_1 | Create a page of order details |  | Sakshi gupta |  | 4 | 2 | 0 | 1 | 1 | 0
Task_2 | Validation |  | Sakshi gupta |  | 5 | 1 | 0 | 0 | 3 | 2
Task_3 | Alert message of successful order |  | Sakshi gupta |  | 4 | 0 | 0 | 0 | 1 | 3
User Story #12 | Payment | 8
Task_1 | Create a page of online payment |  | Mayank |  | 10 | 3 | 0 | 1 | 3 | 3
User Story #13 | Delivery Agents | 13
Task_1 | Create dataBase For agent details |  | Mithun Kumar |  | 4 | 2 | 0 | 2 | 0 | 0
Task_2 | Create a page for adding agent details |  | Mithun Kumar |  | 4 | 2 | 0 | 2 | 0 | 0
Task_3 | Assigning of agent |  | Mithun Kumar |  | 4 | 1 | 0 | 0 | 2 | 2
Task_4 | Validation & Updation |  | Mayank |  | 4 | 0 | 0 | 0 | 2 | 2
User Story #14 | Address details | 13
Task_1 | Create database for address details |  | Md. Siddiq |  | 4 | 1 | 0 | 3 | 0 | 0
Task_2 | Create page for address details |  | Md. Siddiq |  | 5 | 3 | 0 | 2 | 0 | 0
User Story #15 | Finalise order | 5
Task_1 | Confirmation of successful order |  | Sakshi gupta |  | 8 | 0 | 0 | 2 | 3 | 3
User Story #16 | User details | 13
Task_1 | Create dataBase For user details |  | Abhijeet |  | 5 | 2 | 0 | 3 | 0 | 0
Task_2 | Create page for user details |  | Abhijeet |  | 5 | 2 | 0 | 0 | 1 | 2
User Story #17 | Reviews | 8
Task_1 | Create page for reviews |  | Mithun Kumar |  | 8 | 2 | 0 | 2 | 2 | 2
User Story #18 | Customer receives order | 5
Task_1 | Confirmation of successful delivery |  | Abhijeet |  | 8 | 0 | 0 | 2 | 3 | 3
TOTAL |  |  |  |  | 91 | 23 | 0 | 23 | 23 | 24

## Sprint -3
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1
Task_1
Task_2
Task_3
Task_4
User Story #2
Task_1
Task_2
Task_3
Task_4
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Data (hidden)
In-Progress
Completed
N/A